## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
cbYQM5OIgkKBFDofYIWyXmQAAV8R | Non Course Block (Creation) | Submission 7 | Completed | Medium | Owen Erhumuse Yesuf;Chizaram Ikpo | Chukwuemeka Benedict Anyanwu | 12/06/2024 | 11/11/2024 | 12/06/2024 | false | false | 12/06/2024 | Chizaram Ikpo |  |  |  | Under this section, we will be implementing the feature to enable creation of non-course blocks.
nK0F8iMSyEmaYYa0Nlj_1GQAMmFg | General Evaluations - ALL | Submission 7 | Completed | Medium | Dawit Getachew;Owen Erhumuse Yesuf;Chizaram Ikpo;Chukwuemeka Benedict Anyanwu | Chukwuemeka Benedict Anyanwu | 12/06/2024 | 11/23/2024 | 12/06/2024 | false | false | 12/06/2024 | Chizaram Ikpo |  |  |  | This is a general evaluation meeting to meet and evaluate the progress thus far.
6npGZ0B9pE2Zmiln4Y8QzGQADCp1 | Non-Course Blocks (Conflicts Detection & Resolution) | Submission 7 | Completed | Medium | Owen Erhumuse Yesuf;Chizaram Ikpo | Chukwuemeka Benedict Anyanwu | 12/06/2024 | 11/13/2024 | 12/06/2024 | false | false | 12/06/2024 | Chizaram Ikpo |  |  |  | Integrating conditions to observe, detect and report possible conflicts that can occur with course and/or other non-course blocks.
eDHw1n3Ke0-uQG7ztIjkZ2QAMmG6 | Non-Course Blocks (Addition) | Submission 7 | Completed | Medium | Owen Erhumuse Yesuf;Chizaram Ikpo | Chukwuemeka Benedict Anyanwu | 12/06/2024 | 11/11/2024 | 12/06/2024 | false | false | 12/06/2024 | Chizaram Ikpo |  |  |  | This entails implementing the addition of previously created non-course blocks to groups.
VA-3w1ZvJE2yQ4RnDWB9BWQAH2PN | Exploring Out Key Areas to Improve on from Subm 2 - ALL | Submission 7 | Completed | Medium | Dawit Getachew;Owen Erhumuse Yesuf;Chizaram Ikpo;Chukwuemeka Benedict Anyanwu | Chukwuemeka Benedict Anyanwu | 12/06/2024 | 11/10/2024 | 12/06/2024 | false | false | 12/06/2024 | Chukwuemeka Benedict Anyanwu
cGHXX_vwbUWivHwANw2O4WQAGsKc | Submission Overview and Assessment - ALL | Submission 7 | Completed | Medium | Dawit Getachew;Owen Erhumuse Yesuf;Chizaram Ikpo;Chukwuemeka Benedict Anyanwu | Chukwuemeka Benedict Anyanwu | 12/06/2024 | 11/09/2024 | 12/06/2024 | false | false | 12/06/2024 | Dawit Getachew |  |  |  | Here we are performing an overall assessment of the required submission and analyzing possible tasks to be implemented.
Ptesk6T2ekGx67vgKrtZ72QAHmAu | Course Time Slots (Development) | Submission 7 | Completed | Medium | Dawit Getachew;Chukwuemeka Benedict Anyanwu | Chukwuemeka Benedict Anyanwu | 12/06/2024 | 11/17/2024 | 12/06/2024 | false | false | 12/06/2024 | Chukwuemeka Benedict Anyanwu |  |  |  | In this task, the functionality to assign more than one time slots for courses will be developed and integrated.
ZqWhdwIcPEOI2uGQbQ380mQANE-r | Course Time Slots (Conflict Detection and Resolution) | Submission 7 | Completed | Medium | Dawit Getachew;Chukwuemeka Benedict Anyanwu | Chukwuemeka Benedict Anyanwu | 12/06/2024 | 11/22/2024 | 12/06/2024 | false | false | 12/06/2024 | Chukwuemeka Benedict Anyanwu |  |  |  | As this feature allows multiple timing, there's an increased risk of conflicts. The program will be updated to perform adequate checks for possible conflicts that may occur.
eqXtS8K8k0OplBz-5Q_VbWQAJKgf | Updating the Schedule Display. | Submission 7 | Completed | Medium | Dawit Getachew;Chizaram Ikpo | Chukwuemeka Benedict Anyanwu | 12/06/2024 | 11/18/2024 | 12/06/2024 | false | false | 12/06/2024 | Dawit Getachew |  |  |  | With the tons of features being added into the tool, the generated schedule will be updated to reflect these changes.
8RfYEIyqq0qjMNTEcsG_zWQAA_KT | Software Overview - ALL | Submission 7 | Completed | Medium | Dawit Getachew;Owen Erhumuse Yesuf;Chizaram Ikpo;Chukwuemeka Benedict Anyanwu | Chukwuemeka Benedict Anyanwu | 12/06/2024 | 11/30/2024 | 12/06/2024 | false | false | 12/06/2024 | Dawit Getachew |  |  |  | Here we gather as a team to evaluate all implemented functionality and input final modifications to the software.
RKZOops26EWKb11ZUJU9eGQAOvRo | Software Testing Scenario | Submission 7 | Completed | Medium | Dawit Getachew;Chizaram Ikpo | Chukwuemeka Benedict Anyanwu | 12/06/2024 | 12/01/2024 | 12/06/2024 | false | false | 12/06/2024 | Dawit Getachew |  |  |  | Preparing a sample scenario where the client (lecturer i this case) can test our software. A list of steps will be provided in a particular order, explicitly describing what the client will do in each step.
pc11ywiNm0eRiKvsSMsj2WQALFEc | Save-To-File Feature | Submission 7 | Completed | Medium | Owen Erhumuse Yesuf;Chukwuemeka Benedict Anyanwu | Chukwuemeka Benedict Anyanwu | 12/06/2024 | 11/23/2024 | 12/06/2024 | false | false | 12/06/2024 | Chukwuemeka Benedict Anyanwu | 2/2 | Saving to file;Loading from the saved file |  | Integrating the functionality enable saving of the course schedule into a file.
CuN_PIf4fkmaypZFivrYVGQAAjps | Multi-Grouping | Submission 7 | Completed | Medium | Dawit Getachew;Chukwuemeka Benedict Anyanwu | Chukwuemeka Benedict Anyanwu | 12/06/2024 | 11/16/2024 | 12/06/2024 | false | false | 12/06/2024 | Chukwuemeka Benedict Anyanwu | 3/3 | Adding elements (course or non-course blocks);Creating a group;Updating the conflict detections |  | In the task, we'll be implementing the functionality to allow the creation of multiple course groups to contain multiple course and non-course blocks.

## Plan name
Plan name | CS2043 Team 1
Plan ID | 9eWJ6LiaAkOav1U6Fx_yY2QAG8na
Date of export | 12/06/2024